## TDR System Flow & Status
APCRDA Offline TDR Bond Migration — System Development Status & Workflow Guide
Project Name |  | Tech Stack Focus |  | Active Core Files |  | Project Status
APCRDA TDR Bond Migration |  | Next.js 14, Cerbos, Fabric, Prisma |  | 128 Files |  | Week 3 (Approval Phase)
1. SYSTEM ARCHITECTURE & TECHNOLOGY STACK
Layer | Technology / Framework | Version / Spec | Core Responsibility & Scope | Security & Integration Handshake | Status | Implementation Status Notes
Core Web Application | Next.js 14 (App Router) | React 18 LTS | Server-rendered user interfaces, routing structure, React-Hook-Form bindings, pages for all portals. | Supabase Session Cookies validation inside Next.js Middleware with automatic renewals. | Completed | Framework and layout shells are fully operational; global middleware redirects inactive users.
Identity & Authentication | Supabase Auth | v2.108.2 client | Authenticates farmers via OTP and government officials via employee credentials & simulated NIC SSO. | Generates cryptographically signed JWT tokens parsed on the API routes viagetCurrentUser helper. | Completed | APIs for farmer OTP requests, official credentials matching, and login page wrappers are completed.
Granular Authorization | Cerbos PDP | v0.31.0 gRPC client | Policy-as-code middleware implementing ALLOW/DENY check on each backend route based on user roles and rules. | Queries Cerbos PDP locally via gRPC, evaluates policies (e.g. resource_bond.yaml), and records a unique cerbosCallId. | Completed | 5 major YAML policies (bond, approval, certificate, document, derived roles) compiled and running in Docker.
Database & ORM | Prisma & PostgreSQL | Prisma 5.22, PG 15 | Object-Relational Mapping (ORM) and persistent data storage. Implements tables for bonds, approvals, and logs. | Next.js API routes query the PG database using Prisma Client. Database enforces row-level security constraints. | Completed | Database models seeded successfully with test records (farmers, officials, villages). Schema push active.
Immutable Audit Trail | Hyperledger Fabric | v2.5 Gateway SDK | Decentralized blockchain ledger storing immutable records of bond creation, approvals, and certificate hashes. | Next.js API routes connect via Fabric Gateway, execute chaincode write transactions and record the fabricTxId. | Completed | Chaincode deployment configured to run locally. SDK client handles transactions, fallback mock mode available.
Cryptographic Integrity | Custom HMAC Security | SHA-256 Engine | Generates cryptographic signature hashes for approval steps to construct the audit trail's tamper-proof chain. | Calculates signature = HMAC(prevHash + bondId + actorId + decision) using secure server-side environment keys. | Completed | HMAC module implemented and validated using unit tests. Used to verify that approval history is authentic.
Document Generation | PDFKit | v0.19.1 Engine | Generates high-definition PDF certificates containing Telugu internationalization and official signature marks. | Mints certificate details, generates a secure verification QR code, and outputs a downloadable PDF stream. | Completed | PDF layout template defined with QR check. Successfully integrates Commissioner validation hashes.
Data Entry Frontend | React / Next.js Forms | Next.js Pages | Multi-phase data collection forms (holder details, land coordinates, document uploads) for DEO surveyors. | Validates inputs on client and server using Zod schemas, fetches prefill values, and handles document uploads. | In Progress | Currently refining form validation errors and UI responsiveness in Phase 1, Phase 2, and Phase 3 forms.
2. CODEBASE FILE TREE & IMPLEMENTATION STATUS
Module Area | Relative File Path | Module Type | Core Functionality / Responsibility | Active Features & Logic | Status | Developer / Development Notes
Database Schema | prisma/schema.prisma | ORM Schema | Declares all relational models: TdrBond, BondHolder, BondLandDetail, BondDocument, ApprovalStep, Official, Farmer, AuditLog. | Defines tables, enums (OfficialRole, BondStatus), foreign keys, and indexes for performant queries. | Completed | Fully synchronized with the PostgreSQL database. Used by seed.ts to inject test users.
Middleware | src/middleware.ts | Next.js Edge | Filters unauthorized navigation, inspects JWT validity, handles session refresh, redirects to appropriate portals. | Implements path matching for /deo/*, /official/*, and /farmer/* routes; redirects unauthenticated visitors to login. | Completed | Successfully routing users based on role claims. Logs session updates in the server console.
Authz Rules | cerbos/policies/derived_roles.yaml | Cerbos Policy | Calculates dynamic roles such as bond_owner, l1_approver, l2_approver based on district matching and role level. | Enables context-sensitive evaluation (e.g., surveyor can edit only if bond status is DRAFT and created by them). | Completed | Derived roles policy compiled and validated in Cerbos unit test suites.
Authz Rules | cerbos/policies/resource_bond.yaml | Cerbos Policy | Restricts actions on the TdrBond resource: view, edit, submit, reject, return, delete based on user role and step state. | Ensures only authorized actors can progress a bond status (e.g., DEO can delete only DRAFT status). | Completed | Full access matrix tested against multiple user roles and boundary conditions.
Authz Rules | cerbos/policies/resource_approval.yaml | Cerbos Policy | Declares validation policies governing who can perform actions on the ApprovalStep resource. | Maps levels (1 to 4) directly to roles (Tahsildar, SDC, Director, Commissioner) preventing out-of-order processing. | Completed | Compiled successfully, integrated with gRPC enforcement middleware.
Security Module | src/lib/security/hmac.ts | Utility | Computes HMAC hashes using SHA-256 for approval signatures and anonymizes farmer Aadhaar numbers. | Uses server-only environment secret keys to generate signatures that link sequential approval steps. | Completed | Verified by Jest unit tests. Cryptographically guarantees approval history cannot be modified.
Audit Module | src/lib/audit.ts | Logic Helper | Appends records to the database audit_log table. Chains sequential logs by hashing the previous chain_hash. | Integrates both Cerbos PDP call ID and Fabric blockchain transaction ID into a unified audit timeline. | Completed | Active on state-modifying actions. Standardized formatting enforces trace joins.
Fabric Client | src/lib/fabric/client.ts | Integration | Initializes the gRPC connection to the Hyperledger Fabric gateway and fetches the smart contract instance. | Loads crypto credentials (private keys, certificates) from file system paths; falls back to mock logger in dev. | Completed | Ready for local or staging Fabric peers. TLS configuration verified for client auth.
Fabric Gateway | src/lib/fabric/gateway.ts | Integration | Provides high-level TS interfaces: createBond(), recordApproval(), mintCertificate(), queryBondState() to talk to Fabric ledger. | Submits transactions asynchronously using the Gateway SDK, monitors block commits, and returns transaction hashes. | Completed | Features mock fallback logs for teams working without a running local Fabric instance.
Form Containers | src/components/bond-form/BondEntryForm.tsx | Frontend UI | Parent controller for the 3-phase bond entry wizard. Manages state, handles drafts, and processes submissions. | Controls step transitions, loads existing draft data, displays step navigation bar, and handles form submission errors. | In Progress | Currently adjusting draft auto-save debounce triggers and submission transition loaders.
Form Components | src/components/bond-form/Phase1HolderForm.tsx | Frontend UI | Phase 1: Captures holder details (name, relation, door number, street, village, Aadhaar phone) and triggers KYC OTP. | Runs client-side Zod validation, hooks into Aadhaar validation services, and displays OTP verify modal. | In Progress | Refining OTP request cooldown timer and Aadhaar format masks for the DEO input fields.
Form Components | src/components/bond-form/Phase2LandForm.tsx | Frontend UI | Phase 2: Gathers land details (village, survey number, surrendered area, issued extent, TDR ratio, plot code). | Prefills GIS survey data from the mock GIS server, checks that units are in Sq Yards, and handles ratio fields. | In Progress | Improving prefills when surveyor enters survey number, resolving minor state sync glitches.
Form Components | src/components/bond-form/DocumentUploadPhase.tsx | Frontend UI | Phase 3: Provides PDF file drop zones for required uploads (ownership deeds, sketch, plot allotment, Aadhaar copy). | Interacts with upload API, tracks upload progress, displays file size limits, and shows preview thumbnails. | In Progress | Fixing file drag-and-drop boundary layout issue in Safari and older browser viewports.
Approval UI | src/components/approval/BondReviewPanel.tsx | Frontend UI | Main workspace for official validators. Displays comprehensive bond information, maps, uploaded files, and action actions. | Loads approval steps history, renders Reject/Return/Approve actions, triggers OTP signing, and shows validation alerts. | In Progress | Adding multi-page PDF document viewer widget within the right side of the review screen.
Farmer Dashboard | src/components/farmer/BondStatusTracker.tsx | Frontend UI | Interactive timeline displaying the current status of the farmer's bond and the steps remaining in the approval chain. | Listens to realtime updates, highlights completed stages (green) and pending review stages (blue/grey). | In Progress | Refining step label translations in Telugu (i18n integration sync).
API Routes | src/app/api/auth/otp/request/route.ts | API Route | Generates a 6-digit OTP, hashes it, stores it in the database, and mocks SMS transmission. | Validates input phone numbers via Zod, sets 5-minute expiry, and blocks rapid requests. | Completed | Operational. Integrated with farmer login and holder KYC forms.
API Routes | src/app/api/auth/otp/verify/route.ts | API Route | Validates the submitted OTP. On success, issues a Supabase JWT token and sets cookies. | Matches hash of input with stored OtpRequest, marks OTP as used, and returns profile info. | Completed | Tested, handles edge cases (expired OTPs, double-submit attempts, brute-force limits).
API Routes | src/app/api/bonds/[id]/submit/route.ts | API Route | Transitions a draft bond status to PENDING_L1 and executes the Fabric ledger entry. | Requires Cerbos authorization, triggers CreateBond on blockchain, writes to DB and audit log. | Completed | Integrated with blockchain network. Supports idempotency key safety headers.
API Routes | src/app/api/approvals/[bondId]/approve/route.ts | API Route | Records official approval at Level 1, 2, 3, or 4. Generates signature hash and fabric logs. | Checks Cerbos, verifies OTP signature, calculates HMAC, updates DB status, calls Fabric, updates audit log. | Completed | Verified through manual tests. Triggers state changes and signs transactions successfully.
API Routes | src/app/api/certificates/[bondId]/generate/route.ts | API Route | Creates the final PDF certificate using PDFKit, signs it, uploads to Supabase, and logs on Fabric. | Fetches bond details, renders PDF layout, stamps Commissioner hash, sends to Fabric ledger. | Completed | Successfully outputs standard PDFs with working QR validation links.
3. DETAILED SYSTEM WORKFLOWS & DATA FLOWS (ALL IN ONE INTEGRATED FLOW)
Workflow Group | Step # | Process Step & Actor | Action / Process Description | Files & Endpoints Involved | Technical Handshake & Mechanisms | Status
1. AUTHENTICATION & SESSION | 1.1 | Request Login OTP (Farmer) | Farmer submits their phone number. System matches phone against seeded Aadhaar records to verify registration. | api/auth/otp/request/route.ts | Zod parsing -> DB check -> Generate OTP -> Hash OTP in DB -> Mock SMS dispatch. | Completed
1.1 SESSION MANAGEMENT | 1.2 | Verify Login OTP & Issue JWT | Farmer inputs the received 6-digit OTP code. Server verifies, establishes session, and returns cookie. | api/auth/otp/verify/route.ts | DB lookup -> Match OTP hashes -> Generate Supabase JWT -> Set httpOnly cookie session. | Completed
1.1 SESSION MANAGEMENT | 1.3 | Official Credentials / SSO Login | Officials login via simulated National Informatics Centre (NIC) SSO or employee credentials. | api/auth/official/login/route.ts | Verify employee credentials against Official table -> Set JWT with claims (role, districtCode). | Completed
1.1 SESSION MANAGEMENT | 1.4 | Middleware Access Control Check | Next.js middleware interceptor parses the session cookie, checks expiration, and validates routing scopes. | src/middleware.ts | Decrypt JWT token -> Extract role claims -> Match routing pattern (e.g. /deo/*) -> Slide session cookie. | Completed
2. DEO 3-PHASE DATA ENTRY | 2.1 | Create Draft Bond (Phase 1) | DEO Surveyor inputs basic holder details. Fills name, relationship, door number, and Aadhaar phone. | deo/bonds/new/page.tsx, Phase1HolderForm.tsx, api/bonds/route.ts | Checks create permissions via Cerbos PDP -> Hash Aadhaar via HMAC -> Encrypt Aadhaar -> Insert TdrBond (DRAFT). | In Progress
2.2 DATA COLLECTION WIZARD | 2.2 | GIS Prefill & Survey Info (Phase 2) | DEO enters the survey number and village name. The application pre-fills geographical survey area details. | Phase2LandForm.tsx, api/bonds/prefill/[surveyNo]/route.ts | Fetch GIS coordinates from mock external GIS adaptor -> Validate unit is in Sq Yards -> Update TdrBond record. | In Progress
2.2 DATA COLLECTION WIZARD | 2.3 | Document Upload & Hashing (Phase 3) | DEO uploads ownership deeds, surveyor sketch, and Aadhaar copy as PDF files. | DocumentUploadPhase.tsx, api/documents/upload/route.ts | Parse file stream -> Compute SHA-256 hash -> Store PDF in Supabase Storage -> Mock IPFS CID -> Save BondDocument. | In Progress
2.2 DATA COLLECTION WIZARD | 2.4 | Submit Draft Bond for Review | DEO clicks Submit. The bond undergoes strict final validation and enters the approval pipeline. | BondEntryForm.tsx, api/bonds/[id]/submit/route.ts | Zod schema check -> Enforce create permissions -> Write status PENDING_L1 -> Submit Fabric CreateBond -> Chain audit log. | In Progress
3. 5-LEVEL APPROVAL CHAIN | 3.1 | Fetch Review Queue (Official) | Official logs in and views their dashboard queue. The list shows only bonds pending validation at their specific level. | official/queue/page.tsx, api/approvals/queue/route.ts | Extract official's role & district from JWT -> Query Prisma for pending items matching role constraints (Level 1-4). | Completed
3.1 APPROVAL PIPELINE | 3.2 | Open Review Workspace | Official opens the review panel for a specific bond, showing data, GIS mapping preview, and documents. | official/bonds/[id]/review/page.tsx, BondReviewPanel.tsx | Query full TdrBond relational details -> Fetch documents from storage -> Render side-by-side workspace. | In Progress
3.1 APPROVAL PIPELINE | 3.3 | Request Approval OTP (Signing) | Official triggers OTP to their official registered phone number to validate their signature identity. | api/auth/approval-otp/request/route.ts | Validate actor identity -> Generate OTP -> Hash OTP in DB -> Mock official SMS transmission. | Completed
3.1 APPROVAL PIPELINE | 3.4 | Process Approval / Transition | Official enters OTP and submits decision. System validates, signs transaction, and routes to next level. | api/approvals/[bondId]/approve/route.ts | Verify OTP -> Call Cerbos PDP -> Compute approval signature HMAC -> Log to Fabric -> Write Postgres audit log. | Completed
3.1 APPROVAL PIPELINE | 3.5 | Return Bond to Previous Step | If data is incorrect, validator returns the bond to the previous level or back to the DEO for corrections. | api/approvals/[bondId]/return/route.ts | Call Cerbos PDP -> Record decision (RETURNED) -> Set status to previous level or DRAFT -> Fabric & Audit log updates. | Completed
3.1 APPROVAL PIPELINE | 3.6 | Reject Bond Permanently | Official rejects the bond due to mismatching legal records. This terminates the workflow path. | api/approvals/[bondId]/reject/route.ts | Call Cerbos PDP -> Record decision (REJECTED) -> Set status to REJECTED -> Fabric ledger record -> Audit log update. | Completed
4. CERTIFICATE GENERATION | 4.1 | Final Level 4 Commissioner Approval | Commissioner signs and issues final approval, prompting state transition to ACTIVE. | api/approvals/[bondId]/approve/route.ts | Transition bond state to ACTIVE -> Trigger certificate generator trigger asynchronously. | Completed
4.1 CERTIFICATE GENERATION | 4.2 | Generate PDF Certificate | System renders high-quality certificate PDF with Andhra Pradesh emblem and digital QR code. | lib/pdf/certificate.ts, api/certificates/[bondId]/generate/route.ts | PDFKit renders document -> Embed layout details -> Generate QR linking to verify/[tdrNumber] -> Stream PDF. | Completed
4.1 CERTIFICATE GENERATION | 4.3 | Sign Certificate & Store File | System signs PDF with simulated Commissioner digital signature, uploads to storage, and generates hash. | api/certificates/[bondId]/generate/route.ts | Calculate SHA-256 of PDF -> Generate signature HMAC -> Write to Supabase bucket -> Fetch IPFS CID mock. | Completed
4.1 CERTIFICATE GENERATION | 4.4 | Mint Certificate on Blockchain | System binds the generated certificate IPFS CID and signature hash to the blockchain ledger. | lib/fabric/gateway.ts (mintCertificate) | Execute MintCertificate transaction on Fabric ledger -> Save fabricTxId and certificateIpfsCid to PostgreSQL. | Completed
4.1 CERTIFICATE GENERATION | 4.5 | Farmer Download / PWA Download | Farmer logs into PWA, views their issued certificates, and downloads PDF via phone OTP. | farmer/certificates/[id]/page.tsx, api/certificates/[bondId]/download/route.ts | Validate OTP -> Fetch PDF from Supabase Storage -> Stream file download to user browser. | Completed
4.1 CERTIFICATE GENERATION | 4.6 | Public QR Code Verification | Third-parties scan the certificate QR code, opening a public page that checks the ledger's authenticity. | verify/[tdrNumber]/page.tsx, api/certificates/[bondId]/verify/route.ts | Read tdrNumber -> Query DB details -> Query Fabric ledger -> Assert hashes match -> Display verified badge. | Completed
5. THREE-LAYER AUDIT INTEGRITY | 5.1 | Record Cerbos Decision Logs | Every authorization enforce check writes allow/deny decisions with exact policy logic inputs. | src/lib/cerbos/enforce.ts | Cerbos PDP engine prints structured decision logs with cerbosCallId to audit file system. | Completed
5.2 AUDITING MECHANISMS | 5.2 | Build Database Hash-Chain | Every state modification writes a record to the PostgreSQL audit_log table, chaining to the previous log. | src/lib/audit.ts | Fetch latest audit log chain_hash -> Compute new chain_hash = SHA256(prevChainHash + data) -> Insert record. | Completed
5.2 AUDITING MECHANISMS | 5.3 | Submit Ledger Record | Every state transition, approval step signature, and certificate mint is recorded on the Fabric ledger. | src/lib/fabric/gateway.ts | Submit transactions to blockchain network -> Store peer-verified fabricTxId inside Database tables. | Completed
5.2 AUDITING MECHANISMS | 5.4 | Run Integrity Scan Check | Operational scripts scan the PostgreSQL audit logs and cross-reference hashes with the Fabric ledger. | scripts/pre-launch-check.sh, api/health/route.ts | Walk DB audit table -> Verify hashes sequence -> Assert DB data aligns with blockchain transactions -> Alert on mismatch. | Completed